## Sheet1
Task | Description | Predecessors | Duration Estimates |  |  | Expected Duration | Variance
|  |  | Optimistic | Pessimistic | Likely
A | Requirements | N/A | 6 | 12 | 9 | 9 | 1
B | Software | A | 5 | 12 | 8 | 8.1667 | 1.3611
C | Hardware | A | 7 | 13 | 9 | 9.3333 | 1
D | Training | A | 12 | 18 | 14 | 14.3333 | 1
E | Implementation | B, C | 3 | 7 | 5 | 5 | 0.44444
F | Testing | E | 4 | 9 | 5 | 5.5 | 0.69444
[6 empty] | Total Duration | Total Variance | Target Date | Z-Score | Probability of Target
[6 empty] | 28.8333 | 3.1389 | 28 | -0.47036 | 31.9%
[6 empty] | 28.8333 | 3.1389 | 29 | 0.094072 | 53.75%
[6 empty] | 28.8333 | 3.1389 | 30 | 0.6585 | 74.49%
[6 empty] | 28.8333 | 3.1389 | 31 | 1.2229 | 88.93%
[6 empty] | 28.8333 | 3.1389 | 32 | 1.7874 | 96.31%
[6 empty] | 28.8333 | 3.1389 | 33 | 2.3518 | 99.07%